## week1-2
Computer Science 2 Project | Team Members: | Brillo
Group Progress Report |  | Nacaytuna
4th Quarter |  | Udtohan
Week 1 and 2 - Mar 2-13, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Focus on other subjects first due to amount of activities and projects | Some user inputs still bug the code | Was able to fix some bugs in the first week
Try to improve the code if we have free time | Code lacks ability to take in other user inputs for some parts | Was not able to improve the code in the second week due to other subjects
STRENGTH
Code is able to run smoothly
Good coordination
Code can respond to most user inputs
AREAS FOR DEVELOPMENT
Time management
Errors in code after user inputs something that was not considered
User interface design
STRATEGY FOR SUCCESS
Focus and do all activities for other subjects first so we have time to improve our code during weekends or after school
Let others try our code and see if it is successful, if not we will improve our code further
Have good teamwork

## week3-4
Computer Science 2 Project | Team Members: | Brillo
Group Progress Report |  | Nacaytuna
4th Quarter |  | Udtohan
Week 3 and 4 - March 16-27, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Start working on the design for the user interface(e.g. Front end and back end) | Code is only being pasted on programiz and other python compilers and does not have a proper design | Started working on researching on how to start it and also started making drafts in the 3rd week
Improve code and fix possible loopholes | User can be unsatisfied from program outputs | Improved drafts and started showing others our work to get their feedback and tips in the 4th week
Improve code to be able to satisfy user with better and clearer inputs |  | Started to get more satisfaction from other users we gave our code to test
STRENGTH
Code runs smoothly
User interface design drafts seem to be working effectively
Code can take in more user inputs compared to before
People seem to be satisfied when testing our code
AREAS FOR DEVELOPMENT
User Interface Design
Code bugs
Time management
Program dialogue
STRATEGY FOR SUCCESS
Seeking inspiration from others by learning how they made their interface designs so we can try to implement what they did in the process of making ours
Research on various other user interface designs
Experimentation and Drafts

## week5-6
Computer Science 2 Project | Team Members: | Brillo
Group Progress Report |  | Nacaytuna
4th Quarter |  | Udtohan
Week 5 and 6 - March 30-April 3, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Experiment and test UI's we discovered | After the project-check in we learned that some features in our code were problematic and some were just not fit for our program overall so we have to delete them | We were able to fix some features but not yet delete the unfit ones as we are still trying to make them fit for our program
Fix program features | We researched how professionals do simple frameworks | We were able to settle on a simple UI for now but it is only temporary
Remove unnecessary features
STRENGTH
Code runs smoothly
Features were improved
Code now seems more appealing
AREAS FOR DEVELOPMENT
Code UI
Code Features
Program Instructions
STRATEGY FOR SUCCESS
Proper Time management
Experiments and Proper research
Learn from pros and fellow classmates

## week7
Computer Science 2 Project | Team Members: | Brillo
Group Progress Report |  | Nacaytuna
3rd Quarter |  | Udtohan
Week 7 - April 6-11, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS